## Sheet1
|  |  |  | Benefits |  |  |  | Costs |  | Budget1
Category | Type | Project | Description/Status | Area of Benefits | Site Storage (static) | Dynamic Storage | Inflow Capacity | Cost | Cost per ac-ft | Already Expended | District Cost | Unfunded
Short-term (within 6 months) | Send more water south | Alternative operational approaches/pathways to send more water south- Gravity | *The primary water control system was designed to serve two primary functions; Flood Control and Water Supply. There are a number of water control structures along the eastern perimeter of the Water Conservation Areas (WCAs). Their normal operation is to provide water stored in the WCAs to the Lower East Coast to supplement groundwater recharge to the surficial aquifer. During high water conditions these structures are commonly used under normal operations to bleed excess water (above the regulation schedules) from the WCAs and discharge this excess to tide via the Lower East Coast canals. When these operations occur during the wet season, they are typically suspended during rainfall events in order to avoid exacerbating flooding in the local drainage basins. These operational costs are covered in the SFWMD annual budget. | Throughout system |  | 3,800 ac-ft/day |  |  | NA | No costs | No costs | No costs
| Send more water south | Alternative operational approaches/pathways to send more water south- Pumped | *These operations outline the extraordinary efforts required of the existing system infrastructure to attempt to mitigate the damaging estuary flows and high stages in the WCAs by moving excess water south to Everglades National Park and tide. In this context, these means maximizing the use of critical pump stations to move excess water from the WCAs, thereby reducing their stages, so that additional Lake Okeechobee flows can be sent south. | Throughout system |  | 3,300-10,000 ac-ft/day 2 |  |  | $0.30-4.50 ac-ft |  |  | 2268400
| Send more water south | Alternative operational approaches/pathways to send more water south- ENP Enhanced Flow/New Structures | *Since the construction of the Central and South Florida Flood Control Project, two major constraints to moving water south into Everglades National Park have been documented that restrict southerly discharges at the S-12 structures under Tamiami Trail. These include 1) conveyance restrictions at S-12 structures and 2) Conveyance restrictions at Old Tamiami Trail. Two emergency projects are proposed to address these constraints: 1) vegetation removal at S-12A and S-12B and 2) Cutting a new gap in Old Tamiami Trail. | Throughout system |  | 500 ac-ft/day |  | 76000 |  | 10000 |  | 66000
*Vegetation Removal at S-12A and B This project proposes cutting a series open swaths from the clear areas downstream of S-12A & B thru the existing vegetative 'halos' to provide a low resistance flow path for water moving south from the structures. This additional flow capacity will help remove excess water from WCA-3A, which would lower stages and would result in conditions more favorable to moving water from Lake Okeechobee to the WCAs and ultimately Everglades National Park and/or to tide via the East Coast Canal. *Cut New Gap in Old Tamiami Trail In an effort to further enhance southerly flow, this project proposes constructing a large gap in the Old Tamiami Trail downstream of S-12D. The proposed cut is approximately 200 ft. south of the existing S-12E structure under Tamiami Trail. A temporary bridge (to be installed by the U.S. Army Corps of Engineers) will preserve access to the Old Trail for maintenance of electrical power distribution lines that currently serves the Tribal Reservation.
Short-Term | Emergency Storage on Public Lands | C-43 Site | * This is the site for the future CERP C-43 Reservoir Project which is currently awaiting Congressional authorization and appropriation. In the interim, the site is being used for emergency storage. | Caloosahatchee | 1,250 ac-ft |  | 300 ac-ft/day |  | $10 ac-ft | 50000 |  | 180000
* Site was prepped and pumps were installed and have been operating. This provides additional funding to allow extended emergency operations.
Short-Term | Emergency Storage on Public Lands | Boma | *This is the site for a future water quality improvement project. The lands were acquired by the State and Lee County. In the interim, the site is being used for emergency storage. | Caloosahatchee | 686 ac-ft |  | 26.4 ac-ft/day |  | $27 ac-ft | 4100 |  | 57125
*Site has been prepped and pumps were installed and have been operating to pull water from the C-43 Canal (Caloosahatchee River) into two existing agricultural above ground impoundments. This provides additional funding to allow extended emergency operations.
Short-Term | Emergency Storage on Public Lands | C-23/24 | *This is the site for the future CERP IRL-S C-23/24 Reservoir/STA Project which has been authorized by Congress, but is currently awaiting appropriations. In the interim, the site is being used for emergency storage. | St Lucie | 500 ac-ft |  | 59.5-150 ac-ft/day |  | $5.44 ac -ft | 40000 |  | 98000
* Water levels on site are being held higher utilizing existing water control structures. Site conditions will continue to be assessed to determine if a pump can be added to store more water onsite without impacts to adjacent properties.
Short-Term | Emergency Storage on Public Lands | Allapattah | *These lands were acquired for the CERP IRL-S Natural Lands project. In the interim, the site is being used for emergency storage. | St Lucie | 1,600 ac-ft | [5 empty] | No Costs | No Costs
*Water levels on site are being held higher utilizing existing water control structures.
Short-Term | Emergency Storage on Public Lands | HoleyLand/Rotenberger | * Currently Holeyland is approximately one foot over its regulation schedule and Rotenberger is at its regulation schedule. However, recently water levels have been dropping and the maximum stage in both regulation schedules shifts upwards in the coming months, so opportunities for storage will need to be tracked in the near future. | Everglades, Caloosahatchee, St Lucie | 32,000 ac-ft |  | 600 ac-ft/day | 100000 |  |  |  | 100000
* Water levels greater than the regulation schedule can have impacts to wildlife. Increasing water levels above the regulation schedule will require coordination/approval by Florida Fish and Wildlife Conservation Commission.
Short-Term | Emergency Storage on Private Lands | Emergency Storage Contracts | * Working with landowners to identify opportunities for additional emergency storage on private lands. These projects typically involve utilizing existing infrastructure to pump regional water onto private property. Landowners are typically reimbursed for their direct cost (e.g., fuel costs, maintenance). Currently the SFWMD has contracts with two landowners for emergency storage. | Caloosahatchee, St Lucie, Okeechobee, Everglades | TBD | TBD | TBD |  | $25-50 ac-ft | TBD | 50000 | 200000
Short-term | Emergency Storage on Private Lands | Lost Oak Ranch | * Project has received Corps permit and is currently under construction. Anticipate project to be fully operational within the next month. | Okeechobee |  | 374 ac-ft/yr |  | $629,073 (10 yr costs) |  |  | $354,073 (1st five years of contract)
Short-term | Emergency Storage on Private Lands | Triple A Ranch | * High water conditions are currently hindering completion of the project. Project will be completed after high water levels subside after the wet season. The site is currently holding a significant amount of water. | Okeechobee |  | 397 ac-ft/yr |  | $607,186 (10 yr costs) |  |  | $472,186 (1st five years of contract)
Short-Term | Lake Okeechobee Stage Management | Reevaluate LORSS Risk Assessment 3 | * Reevaluate the risk assessment conducted for LORSS to determine if recent repairs to the dike and associated culverts have reduced risk to the point that USACE could utilize operational discretion within LORSS to reduce discharges to tide. | Throughout system |  |  |  | staff time
Total for Short-Term | [9 empty] | 104100 | 876259 | 2969525
1 Budget numbers assume emergency efforts continue through the end of the calendar year (December 2013).
2 Ac-ft varies depending on hydrologic conditions and STA treatment capacity. STA diversion may be necessary under certain conditions.
3 Requires Corps agreement to initiate
4 These costs are probably high and can be reduced (as they include land management and other unrelated expenses)
Mid-Term Actions (6 mo. to 2 years)
CERP Projects: Complete Indian River Lagoon – South Project – Mid-term actions include the construction and operation of a new stormwater treatment area to reduce sediment, phosphorus and nitrogen going to the St. Lucie River estuary and the lagoon. Total project costs are $60M with $20M coming from FY13 and $40M from the Governor’s FY14 Budget. This project will complement the US Army Corps of Engineers construction of the C-44 Reservoir and will expedite completion of the entire project by at least 2 years. Long term activities (over two years) include: Construction and operation of three additional new above ground reservoirs and their connecting canals, control structures, levees and pumps to capture water from the C-23, C-24 and C-25 canals for increased storage; Construction and operation of two additional new stormwater treatment areas to reduce sediment, phosphorus and nitrogen going to the St. Lucie River estuary and the lagoon. STAs are planned for each of the C-23/24 and C-25 basins; Restoration of the upland/wetland mosaic and habitat with ditch plugging, berm construction, and periodic fire maintenance at three locations.; and Redirection of water from the C-23/24 basin to the north fork of the St. Lucie River attenuating fresh water flows to the estuary. Additionally, seek authorization for C-43 Project and the Central Everglades Planning Project.
Interim Storage on Public Lands – The District has acquired lands in the C-43, C-23, C-24, and Allapattah. These lands were acquired for the CERP projects. In the interim, the sites are being used for emergency storage. Existing infrastructure is being utilized to hold water onsite, however significantly more interim storage can be realized if additional work is conducted including ditch filling/canal plugging, berm construction, water control structures, land management, which would allow for more regional water to be pumped and stored onsite.
Interim Storage on Private Lands - The Dispersed Water Management Program encourages property owners to retain water on their land rather than drain it, accept and detain regional runoff, or do both. Holding water on these lands is one tool to reduce the amount of water flowing into Lake Okeechobee during the wet season and discharged to coastal estuaries for flood protection. Private landowner involvement typically includes cost-shared cooperative projects, easements or payment for environmental services. Shallow water retention also provides valuable groundwater recharge for water supply, opportunities for water quality improvement and rehydration of drained systems.